## _REFERENCE888777888
WorkSheet Name | Report Code | Company Id | Job Id | Start Date | End Date | Payroll Subledger | Pay Period Id

## Sample Work
3wePThnL4hDT4Wzth | This is a test API Defect Part 6 | Site | Cleaning | Defect | Standard | 2020-09-26T06:38:17.919Z | X4R4JoXr5rGNFbtsw | mogXDfRsq4EEK9mSo | This is a test API Defect Part 6
3wePThnL4hDT4Wzth | This is a test API Defect Part 7 | Site | Cleaning | Defect | Standard | 2020-09-26T06:38:17.919Z | X4R4JoXr5rGNFbtsw | mogXDfRsq4EEK9mSo | This is a test API Defect Part 7
3wePThnL4hDT4Wzth | This is a test API Defect Part 8 | Site | Cleaning | Defect | Standard | 2020-09-26T06:38:17.919Z | X4R4JoXr5rGNFbtsw | mogXDfRsq4EEK9mSo | This is a test API Defect Part 8
3wePThnL4hDT4Wzth | This is a test API Defect Part 9 | Site | Cleaning | Defect | Standard | 2020-09-26T06:38:17.919Z | X4R4JoXr5rGNFbtsw | mogXDfRsq4EEK9mSo | This is a test API Defect Part 9
3wePThnL4hDT4Wzth | This is a test API Defect Part 10 | Site | Cleaning | Defect | Standard | 2020-09-26T06:38:17.919Z | X4R4JoXr5rGNFbtsw | mogXDfRsq4EEK9mSo | This is a test API Defect Part 10

## Test Data
SMbEYmdCvzKSudE9Y | Building A | Level 11 | Unit 1103 | General Repairs & Maintenance | Water ingress x 2 | 7 windows near Bedroom 2 removed, insulated and reinstated - Monitor condensation | uGpp8FSYcwyxpL7e2 | pPMRdCJ9uCjtdyYhw | HTtZsCZGkA39PnAwm | w8tbGiQquzwCmhN8c | 2020-11-30T06:38:17.919Z | Scheduled | Defect
SMbEYmdCvzKSudE9Y | Building A | Ground | Commercial Unit | General Repairs & Maintenance | Storage required for FM Department | Clean room out and Install Shelves and Racks for FM Department - Marty to tidy and finish room | uGpp8FSYcwyxpL7e2 | Ceqru9BbHpv4sFzB8 | HTtZsCZGkA39PnAwm | w8tbGiQquzwCmhN8c | 2020-11-30T06:38:17.919Z | Scheduled | Defect
SMbEYmdCvzKSudE9Y | Building A | Ground | Plant room | Electron Services | Wall section requires rectification FN:3899 | Marty to sheet walls | uGpp8FSYcwyxpL7e2 | Ceqru9BbHpv4sFzB8 | HTtZsCZGkA39PnAwm | w8tbGiQquzwCmhN8c | 2020-11-30T06:38:17.919Z | Scheduled | Defect
SMbEYmdCvzKSudE9Y | Building A | Ground | Bin Store Room | General Repairs & Maintenance | Water damage - Re-epoxy | Identify leak, repaint epoxy surface - Quote received | uGpp8FSYcwyxpL7e2 | Ceqru9BbHpv4sFzB8 | HTtZsCZGkA39PnAwm | w8tbGiQquzwCmhN8c | 2020-11-30T06:38:17.919Z | Scheduled | Defect
SMbEYmdCvzKSudE9Y | Building A | Level 6 | Unit 603 | General Repairs & Maintenance | Dishwasher | Investigate issue - awaiting panel Marty will follow up | uGpp8FSYcwyxpL7e2 | Ceqru9BbHpv4sFzB8 | HTtZsCZGkA39PnAwm | w8tbGiQquzwCmhN8c | 2020-11-30T06:38:17.919Z | Scheduled | Defect
3wePThnL4hDT4Wzth | Ground Floor |  |  | General Repairs & Maintenance | Concrete dusting | Markham to provide 2 options | uGpp8FSYcwyxpL7e2 | Ceqru9BbHpv4sFzB8 | HTtZsCZGkA39PnAwm | w8tbGiQquzwCmhN8c | 2020-11-30T06:38:17.919Z | Scheduled | Defect
3wePThnL4hDT4Wzth | Level 1 | Apartment 102 |  | General Repairs & Maintenance | Water damage and inspection holes to be covered | Allerce engaged to do works - Awaiting reports that roofing has been successful | uGpp8FSYcwyxpL7e2 | Ceqru9BbHpv4sFzB8 | HTtZsCZGkA39PnAwm | w8tbGiQquzwCmhN8c | 2020-11-30T06:38:17.919Z | Scheduled | Defect
3wePThnL4hDT4Wzth | Level 2 | Apartment 203 |  | General Repairs & Maintenance | Remove rust and paint on Balcony | Marty to liaise | uGpp8FSYcwyxpL7e2 | Ceqru9BbHpv4sFzB8 | HTtZsCZGkA39PnAwm | w8tbGiQquzwCmhN8c | 2020-11-30T06:38:17.919Z | Scheduled | Defect
3wePThnL4hDT4Wzth | Ground Floor |  |  | General Repairs & Maintenance | Drencher and Curtain | Decision to be made regarding direction with this | uGpp8FSYcwyxpL7e2 | pPMRdCJ9uCjtdyYhw | HTtZsCZGkA39PnAwm | w8tbGiQquzwCmhN8c | 2020-11-30T06:38:17.919Z | Scheduled | Defect
3wePThnL4hDT4Wzth | Roof |  |  | General Repairs & Maintenance | non compliant roof pitch | Freestyle engaged to do works - Require dry period Cliplock roof sheets installed 3.0degree rake achieved | uGpp8FSYcwyxpL7e2 | pPMRdCJ9uCjtdyYhw | HTtZsCZGkA39PnAwm | w8tbGiQquzwCmhN8c | 2020-11-30T06:38:17.919Z | Scheduled | Defect

## 21-2-20
Date: 21/02/2020 | SITE | AREA/UNIT | ISSUE | ACTIONS | RESPONSIBILITY | PROPOSED DATE | COMPLETED DATE
1 | AERO | 903/766-770 | Dishwasher Cabinetry | No Further Action Required
2 | AERO | Unit 1103 | Water ingress x 2 | Frontline Dan & Steve to inspect | TJ | 2020-02-26
3 | AERO | Unit 402 | Water Leak | Strata left door open, No Further Actions Required |  | 2020-02-19 | 2020-02-19
4 | WATERVIEW | Unit 101 Storage Cage | Water Leak | Remove existing seal, reseal and dry | TJ & MR | 2020-02-21 | 2020-02-21
5 | WATERVIEW | Unit 201 | Water Leak | Water test 21-2-20 | TJ & MR | 2020-02-20 | 2020-02-20
6 | WATERVIEW | Unit 8 | Hand Rail Gap | Frontline Completed |  | 2020-02-19 | 2020-02-19
7 | WATERVIEW | Unit 4 | Water Leak | Modified shroud - Not Completed Why not seal around vent | TJ | 2020-02-21
8 | WATERVIEW | Unit 204 | Water Leak | HV Aluminium & GWH to inspect site | RB, TJ | 2020-02-27
9 | WATERVIEW | Unit 8 Carpark | Firemaster Plus Curtain | Shaun Wallace and Yunguang (Fire engineer) communicating for solution, Greenfire product | RB
10 | SOHO THROSBY ST | 103/27 Lot 6 | Water & Mould Issues | installs back pans,deck tie and press tight | TJ | 2020-02-21 | 2020-02-21
11 | SOHO FERN ST | 404/11 | No overflow | Awaiting EWP training next week | SI | 2020-02-26
12 | CENTRALE | 301B | Expansion Joints | GWH to gain access and inspect | TJ | Early March
13 | CENTRALE | B303 | Water Damage | Awaiting access |  | Early March
14 | EASTSIDE | Unit 603 | Water Leak x 2 | TJ Left message for access | TJ | Early March
15 | EASTSIDE | Unit 410 | Water Leak | TJ Left message for access | TJ | Early March
16 | EASTSIDE | Unit 310 | Water Leak | TJ Left message for access | TJ | Early March
17 | GREENSIDE | 2:04 | Water Sealing | Redo Bathroom - Confirm with Jono | RB & JONO | 2020-02-27
18 | GREENSIDE |  | Cracks | Epoxy preferred less downtime, Tiling would be ideal whether Tiles with linear drains installed at each entry door x 4 are an acceptable solution - Confirm this is acceptable Check with JONO | RB & JONO
19 | DENISON ST | Unit 1 | Water Ingress | TJ arranging access for next week | TJ | 2020-02-26
20 | DENISON ST | Unit 9 | Water Ingress | TJ arranging access for next week | TJ | 2020-02-26
21 | DENISON ST | Common area | Drummy Tiles | Contact TDX to repair | RB | 2020-02-25
22 | MILLHORN |  | Leaking Fire Stairs | To be resealed - Inspection required | TJ | March
23 | MILLHORN | Unit 103 | Veranda Leaking | ONYX to repair light weight cladding failure | TJ | March

## 4-3-20
Date: 2/3/2020 | SITE | AREA/UNIT | ISSUE | ACTIONS | RESPONSIBILITY | PROPOSED DATE | COMPLETED DATE
1 | AERO | Unit 1103 | Water ingress x 2 | Frontline Dan & Steve to inspect - 4 dry days required | TJ | 2020-02-26
2 | AERO | ROOF Storage GWH FM Department | Storage required for FM Department | Clean room out and Install Shelves and Racks for FM Department - Next Week | Marty | 2020-03-12 | Commenced
3 | WATERVIEW | Unit 101 Storage Cage | Water Leak | Remove existing seal, reseal and dry | TJ & MR | 2020-02-21 | 2020-02-21 | Completed
4 | WATERVIEW | Unit 201 | Water Leak | Water test 21-2-20 | TJ & MR | 2020-02-20 | 2020-02-20 | Completed
5 | WATERVIEW | Unit 4 | Water Leak | Modified shroud - Not Completed Why not seal around vent - Friday Pickup | TJ | 2020-02-25
6 | WATERVIEW | Unit 204 | Water Leak | HV Aluminium to reseal area Week 2-3-20 | RB | 2020-03-03
7 | WATERVIEW | Carpark | Concrete dusting | Test Evo-Seal product -TJ Follow up with epoxy and Rick Harris | TJ | 2020-03-09
8 | WATERVIEW | Unit 8 Carpark | Drencher and Curtain | Shaun Wallace and Yunguang (Fire engineer) communicating for solution, HWC to supply Pressure at Street Level, PCA to be engaged Purchase Order TO BE ISSUED | RB | March
9 | THROSBY ST | 103/27 Lot 6 | Water & Mould Issues | installs back pans,deck tie and press tight | TJ | 2020-02-21 | 2020-02-21 | Completed
10 | MAITLAND ROAD ISLINGTON | Entry Foyer | [5 empty] | Completed
11 | SOHO FERN ST | 404/11 | No overflow | Awaiting EWP training next week | SI | 2020-02-26
12 | MAITLAND ROAD ISLINGTON | 401/54 Unit 102 & 402 - 54 | Water & Mould Issues, Water issues planterboxes | Taylor to recommend contractor - 4.30pm inspection today | TJ |  |  | 402 & 102 repair complete,
14 | CENTRALE | 301B | Expansion Joints | GWH to gain access and inspect - Roof leak today | ALERCE | Early March
15 | CENTRALE | B303 & 302A | Water Damage | Awaiting access |  | Early March |  | Completed
16 | EASTSIDE | Unit 603 | Water Leak x 2 | TJ Left message for access | TJ | Early March
17 | EASTSIDE | Unit 310 | Water Leak | TJ Left message for access - Early next week | TJ | Early March
18 | GREENSIDE | 2:04 | Water Sealing | Redo Bathroom - Confirm with Jono after his inspection | RB & JONO | Early March
19 | GREENSIDE |  | Cracks | Epoxy preferred less downtime, Tiling would be ideal whether Tiles with linear drains installed at each entry door x 4 are an acceptable solution - Confirm this is acceptable Confirm with Jono after his inspection | RB & JONO | Early March
20 | DENISON ST HAMILTON | Unit 1 | Water Ingress | TJ arranging access for late next week | TJ | Early March
21 | DENISON ST HAMILTON | Unit 9 & 12 | Water Ingress | TJ arranging access for late next week | TJ | Early March
22 | DENISON ST HAMILTON | Planterboxes | Leaking Planterboxes | TJ arranging access for late next week | TJ | Early March
23 | DENISON ST HAMILTON | Common area | Drummy Tiles | Contact TDX to repair & install expansion joint - Left message try again | TDX | Early March
24 | MILLHORN |  | Leaking Fire Stairs | To be resealed - Inspection required Dan to rectify water leak | TJ | March |  | Complete
25 | MILLHORN | Unit 304 | Veranda Leaking | ONYX to repair light weight cladding failure - Will be repaired next week | TJ | March |  | Near Completion Mould Kill application required
26 | HUNTER CIVILLABS |  |  | * Lock out station screwed to wall (near Grinder) * Dry hooks to be installed near Nuke Container for Tools * Policy Board to be installed in Hallway * Door Closer in Ladies toilet to be replaced * Dust Stopper required for Door leading from front entrance to Lab * White board to be installed * 2 Shelves to be installed above each toilet - Marty to install Friday 6-3-20 | Marty | 2020-03-09 |  | Completed

## 16-3-20
Date: 2/3/2020 | SITE | AREA/UNIT | ISSUE | ACTIONS | RESPONSIBILITY | PROPOSED DATE | COMPLETED DATE
1 | AERO | Unit 1103 | Water ingress x 2 | Frontline Dan & Steve to inspect - 4 dry days required | TJ | 2020-02-26
2 | AERO | ROOF Storage GWH FM Department | Storage required for FM Department | Clean room out and Install Shelves and Racks for FM Department - Next Week | Marty | 2020-03-12 | Commenced
3 | AERO | Unit 402 | Window in living room leaking |  | TJ & Marty
4 | AERO | Some units | GPO's & Switches not sealed correctly? FN: 3894
5 | AERO | HWS Plant Room | Wall section requires rectification FN:3899
6 | AERO | Bin Room | Water damage - Re-epoxy
7 | WATERVIEW | Unit 101 Storage Cage | Water Leak | Remove existing seal, reseal and dry | TJ & MR | 2020-02-21 | 2020-02-21 | Completed
8 | WATERVIEW | Unit 4 | Water Leak | Modified shroud - Not Completed Why not seal around vent - Friday Pickup | TJ | 2020-02-25
9 | WATERVIEW | Unit 204 | Water Leak | HV Aluminium to reseal area Week 2-3-20 | RB | 2020-03-03
10 | WATERVIEW | Carpark | Concrete dusting | Test Evo-Seal product -TJ Follow up with epoxy and Rick Harris | TJ | 2020-03-09
11 | WATERVIEW | Unit 8 Carpark | Drencher and Curtain | Shaun Wallace and Alan Sacarro (Fire engineer) communicating for solution, HWC to supply Pressure at Street Level, PCA engaged Purchase Order HAS BEEN ISSUED | RB | March
12 | THROSBY ST | 103/27 Lot 6 | Water & Mould Issues | installs back pans,deck tie and press tight | TJ | 2020-02-21 | 2020-02-21 | Completed
13 | SOHO FERN ST | 404/11 | No overflow | Awaiting EWP training next week | SI | 2020-03-26
14 | MAITLAND ROAD ISLINGTON | 401/54 Unit 102 & 402 - 54 | Water & Mould Issues, Water issues planterboxes | Taylor to recommend contractor - 4.30pm inspection today | TJ |  |  | 402 & 102 repair complete,
15 | CENTRALE | 301B | Expansion Joints | GWH to gain access and inspect - Roof leak today | ALERCE | Early March
16 | EASTSIDE | Unit 603 | Water Leak x 2 | TJ Left message for access | TJ | Early March
17 | EASTSIDE | Unit 310 | Water Leak | TJ Left message for access - Early next week | TJ | Early March
18 | GREENSIDE | 2:04 | Water Sealing | Redo Bathroom - Confirm with Jono after his inspection | RB & JONO | Early March
19 | GREENSIDE |  | Cracks | Epoxy preferred less downtime, Tiling would be ideal whether Tiles with linear drains installed at each entry door x 4 are an acceptable solution - Confirm this is acceptable Confirm with Jono after his inspection | RB & JONO | Early March
20 | DENISON ST HAMILTON | Unit 1 | Water Ingress | TJ arranging access for late next week | TJ | Early March
21 | DENISON ST HAMILTON | Unit 9 & 12 | Water Ingress | TJ arranging access for late next week | TJ | Early March
22 | DENISON ST HAMILTON | Planterboxes | Leaking Planterboxes | TJ arranging access for late next week | TJ | Early March
23 | DENISON ST HAMILTON | Common area | Drummy Tiles | Contact TDX to repair & install expansion joint - Left message try again | TDX | Early March

## 13-4-2020
Date: 2/4/2020 | SITE | AREA/UNIT | ISSUE | ACTIONS | RESPONSIBILITY | PROPOSED DATE | COMPLETED DATE
1 | AERO | Unit 1103 | Water ingress x 2 | Frontline Dan & Steve to inspect - 4 dry days required | TJ | 2020-02-26
2 | AERO | ROOF Storage GWH FM Department | Storage required for FM Department | Clean room out and Install Shelves and Racks for FM Department - Next Week | Marty | 2020-03-12 | Commenced
3 | AERO | Unit 402 | Window in living room leaking | Inspect & report back 3 windows remaining | Marty | 2020-04-03
4 | AERO | HWS Plant Room | Wall section requires rectification FN:3899 | Marty to sheet walls | Marty
5 | AERO | FM Plant | Make into store | Marty to fit out for Facility team | Marty
6 | AERO | Bin Room | Water damage - Re-epoxy | Identify leak, repaint epoxy surface | Marty
7 | WATERVIEW | Unit 4 | Water Leak | Modified shroud - Not Completed Why not seal around vent - Marty to enquire whether this has stopped water issue | Marty | 2020-02-25 | Not Sure
8 | WATERVIEW | Carpark | Concrete dusting | Test Evo-Seal product -TJ Follow up with epoxy and Rick Harris 4 day required | Marty
9 | WATERVIEW | Unit 8 Carpark | Drencher and Curtain | Shaun Wallace and Alan Sacarro (Fire engineer) communicating for solution, HWC to supply Pressure at Street Level, PCA engaged Purchase Order HAS BEEN ISSUED | RB | March
10 | WATERVIEW | L2 Common Rooves & Soffitt | non compliant roof & no expansion joints in Soffitt | Allerce engaged to do works - Require dry period | RB
11 | THROSBY ST | 103/27 Lot 6 | Water & Mould Issues | installs back pans,deck tie and press tight - Marty to contact Chris Lawler re access | MR
12 | SOHO FERN ST | 404/11 | No overflow | Awaiting EWP training next week | TJ | 2020-03-26
13 | MAITLAND ROAD ISLINGTON | 401/54 Unit 102 & 402 - 54 | Water & Mould Issues, Water issues planterboxes | Taylor to recommend contractor - 4.30pm inspection today Check 401 | MR
14 | CENTRALE | Lvl 2&3 | Water Leak | Rectify ridges & Front strip to prevent water ingress | MR | 2020-04-03
15 | CENTRALE | 305A | Cladding leak | Investigate & Repair - Marty Arrange to inspect | MR
16 | MILLHORN | Apt 304 | Water leak | Investigate & Repair - Flood test | MR | 2020-04-03
17 | CENTRALE | 301B | Expansion Joints | GWH to gain access and inspect - Roof leak today | ALERCE | Early March
18 | EASTSIDE | Unit 603 | Water Leak x 2 | Taylor arranging EWP | TJ | Early March
19 | EASTSIDE | 702 | Inspect balcony above 603 for any water issues | Marty | MR | April
20 | EASTSIDE | Unit 310 | Water Leak | Marty to check balcony of unit above | MR | April
21 | GREENSIDE | 2:04 | Water Sealing | Redo Bathroom - Confirm with Jono after his inspection Access required to inspect | RB & JONO | Early March
22 | GREENSIDE |  | Cracks | Epoxy preferred less downtime, Tiling would be ideal whether Tiles with linear drains installed at each entry door x 4 are an acceptable solution - Confirm this is acceptable Confirm with Jono after his inspection | RB & JONO
23 | CIVILAB |  | Shelves & Room |  |  | 2020-04-03
24 | DENISON ST HAMILTON | Unit 1 | Water Ingress | Marty arranging access for late next week | TJ | April
25 | DENISON ST HAMILTON | Unit 9 & 12 | Water Ingress | Marty arranging access for late next week | TJ | April
26 | DENISON ST HAMILTON | Planterboxes | Leaking Planterboxes | Marty arranging access for late next week | TJ | April
27 | DENISON ST HAMILTON | Common area | Drummy Tiles | Contact TDX to repair & install expansion joint - Left message try again | TDX | April

## 20-4-2020
Date: 2/4/2020 | SITE | AREA/UNIT | ISSUE | ACTIONS | RESPONSIBILITY | PROPOSED DATE | COMPLETED DATE
1 | AERO | Unit 1103 | Water ingress x 2 | Frontline Dan & Steve to inspect - 4 dry days required | TJ | 2020-02-26
2 | AERO | ROOF Storage GWH FM Department | Storage required for FM Department | Clean room out and Install Shelves and Racks for FM Department - Next Week | Marty | 2020-03-12 | Commenced
3 | AERO | Unit 402 | Window in living room leaking | Inspect & report back 3 windows remaining | Marty | 2020-04-03
4 | AERO | HWS Plant Room | Wall section requires rectification FN:3899 | Marty to sheet walls | Marty
5 | AERO | FM Plant | Make into store | Marty to fit out for Facility team | Marty
6 | AERO | Bin Room | Water damage - Re-epoxy | Identify leak, repaint epoxy surface | Marty
7 | WATERVIEW | Unit 4 | Water Leak | Modified shroud - Not Completed Why not seal around vent - Marty to enquire whether this has stopped water issue | Marty | 2020-02-25 | Not Sure
8 | WATERVIEW | Carpark | Concrete dusting | Test Evo-Seal product -TJ Follow up with epoxy and Rick Harris 4 day required | Marty
9 | WATERVIEW | Unit 8 Carpark | Drencher and Curtain | Shaun Wallace and Alan Sacarro (Fire engineer) communicating for solution, HWC to supply Pressure at Street Level, PCA engaged Purchase Order HAS BEEN ISSUED | RB | March
10 | WATERVIEW | L2 Common Rooves & Soffitt | non compliant roof & no expansion joints in Soffitt | Allerce engaged to do works - Require dry period | RB
11 | THROSBY ST | 103/27 Lot 6 | Water & Mould Issues | installs back pans,deck tie and press tight - Marty to contact Chris Lawler re access | MR
12 | SOHO FERN ST | 404/11 | No overflow | Awaiting EWP training next week | TJ | 2020-03-26
13 | MAITLAND ROAD ISLINGTON | 401/54 Unit 102 & 402 - 54 | Water & Mould Issues, Water issues planterboxes | Taylor to recommend contractor - 4.30pm inspection today Check 401 | MR
14 | CENTRALE | Lvl 2&3 | Water Leak | Rectify ridges & Front strip to prevent water ingress | MR | 2020-04-03
15 | CENTRALE | 305A | Cladding leak | Investigate & Repair - Marty Arrange to inspect | MR
16 | MILLHORN | Apt 304 | Water leak | Investigate & Repair - Flood test | MR | 2020-04-03
17 | CENTRALE | 301B | Expansion Joints | GWH to gain access and inspect - Roof leak today | ALERCE | Early March
18 | EASTSIDE | Unit 603 | Water Leak x 2 | Taylor arranging EWP | TJ | Early March
19 | EASTSIDE | 702 | Inspect balcony above 603 for any water issues | Marty | MR | April
20 | EASTSIDE | Unit 310 | Water Leak | Marty to check balcony of unit above | MR | April
21 | GREENSIDE | 2:04 | Water Sealing | Redo Bathroom - Confirm with Jono after his inspection Access required to inspect | RB & JONO | Early March
22 | GREENSIDE |  | Cracks | Epoxy preferred less downtime, Tiling would be ideal whether Tiles with linear drains installed at each entry door x 4 are an acceptable solution - Confirm this is acceptable Confirm with Jono after his inspection | RB & JONO
23 | CIVILAB |  | Shelves & Room |  |  | 2020-04-03
24 | DENISON ST HAMILTON | Unit 1 | Water Ingress | Marty arranging access for late next week | TJ | April
25 | DENISON ST HAMILTON | Unit 9 & 12 | Water Ingress | Marty arranging access for late next week | TJ | April
26 | DENISON ST HAMILTON | Planterboxes | Leaking Planterboxes | Marty arranging access for late next week | TJ | April
27 | DENISON ST HAMILTON | Common area | Drummy Tiles | Contact TDX to repair & install expansion joint - Left message try again | TDX | April

## 1-5-20
Date: 2/4/2020 | SITE | AREA/UNIT | ISSUE | ACTIONS | RESPONSIBILITY | PROPOSED DATE | COMPLETED DATE
1 | AERO | Unit 1103 | Water ingress x 2 | Frontline Dan & Steve to inspect - 4 dry days required | TJ | 2020-02-26
2 | AERO | ROOF Storage GWH FM Department | Storage required for FM Department | Clean room out and Install Shelves and Racks for FM Department - Marty to tidy and finish room | Marty | 2020-03-12 | Commenced
3 | AERO | Unit 402 | Window in living room leaking | Inspect & report back 3 windows remaining | Marty | 2020-04-03
4 | AERO | HWS Plant Room | Wall section requires rectification FN:3899 | Marty to sheet walls | Marty
5 | AERO | FM Plant | Make into store | Marty to fit out for Facility team | Marty
6 | AERO | Bin Room | Water damage - Re-epoxy | Identify leak, repaint epoxy surface | Marty
| AERO | ROOF above BBQ | Water issue - awning | Seal awning to building with Mastik | Marty | Completed
8 | WATERVIEW | Carpark | Concrete dusting | Test Evo-Seal product -TJ Follow up with epoxy and Rick Harris 4 day required | Marty
9 | WATERVIEW | Unit 8 Carpark | Drencher and Curtain | Shaun Wallace and Alan Sacarro (Fire engineer) communicating for solution, HWC to supply Pressure at Street Level, PCA engaged Purchase Order HAS BEEN ISSUED | RB | March
10 | WATERVIEW | L2 Common Rooves & Soffitt | non compliant roof & no expansion joints in Soffitt | Allerce engaged to do works - Require dry period | RB
11 | THROSBY ST | 103/27 Lot 6 | Water & Mould Issues | installs back pans,deck tie and press tight - Marty to contact Chris Lawler re access | Marty | Early May
12 | SOHO FERN ST | 404/11 | No overflow | Marty to schedule spitter install | Marty | 2020-03-26
13 | MAITLAND ROAD ISLINGTON | 401/54 Unit 102 & 402 - 54 | Water & Mould Issues, Water issues planterboxes | Taylor to recommend contractor - 4.30pm inspection today Check 401 Marty following up with Tenant | Marty
14 | MAITLAND ROAD ISLINGTON | East & West prefab walls | Install Backing rod and Mastik | Marty to ensure 3 point system anchoring is adhered to | Marty
15 | CENTRALE | Lvl 2&3 | Water Leak | Rectify ridges & Front strip to prevent water ingress | Marty | 2020-04-03
16 | CENTRALE | 305A | Cladding leak | Investigate & Repair - Marty Arrange to inspect - Allerce Marty to follow up | Marty
17 | CENTRALE | A303 | Common area wall warp, carpet soiled | Investigate & Repair - Marty Arrange to inspect Tenant advised no issue | Marty
18 | CENTRALE | A302 | Water leak | Investigate & Repair - Marty Arrange to inspect | Marty | Completed
19 | CENTRALE | B303 | Water damage Kitchen | Investigate & Repair - Marty Arrange to inspect | Marty
20 | CENTRALE | B103 | Ensuite Bathroom | Marty Arrange to inspect | Marty
21 | CENTRALE | A106 | Cracking | Investigate & Repair - Marty Arrange to inspect | Marty
22 | CENTRALE | A303 | Mould smell outside 303 | Investigate & Repair - Marty Arrange to inspect | Marty
23 | CENTRALE | A303 | Window leak | Investigate & Repair - Marty Arrange to inspect | Marty
24 | CENTRALE | B202 | Cracking | Investigate & Repair - Repaired ready to paint | Marty
25 | CENTRALE | B202 | Loose tiles on Balcony | Investigate & Repair - Marty Arrange to inspect | Marty | Completed
26 | MILLHORN | Apt 304 | Water leak | Investigate & Repair - Flood test | Marty | 2020-04-03
27 | CENTRALE | 301B | Expansion Joints | GWH to gain access and inspect - Roof leak today | Marty | Early March
28 | EASTSIDE | Unit 603 | Water Leak x 2 | Taylor arranging EWP - ONYX | TJ | Early March | Wait after Restrictions have been lifted
29 | EASTSIDE | 702 | Inspect balcony above 603 for any water issues | Taylor given Natasha Contact | MR & TJ | April | Wait after Restrictions have been lifted
30 | EASTSIDE | Unit 310 | Water Leak | Marty to check balcony of unit above - await COVID19 restrictions to be lifted | MR | April | Wait after Restrictions have been lifted
31 | GREENSIDE | 2:04 | Water Sealing | Redo Bathroom - Confirm with Jono after his inspection Access required to inspect | RB & JONO | Early March
32 | GREENSIDE |  | Cracks | Epoxy preferred less downtime, Tiling would be ideal whether Tiles with linear drains installed at each entry door x 4 are an acceptable solution - Confirm this is acceptable Confirm with Jono after his inspection | RB & JONO
33 | CIVILAB |  | Shelves & Room | Marty to contact Allerce | Marty | 2020-04-03
34 | DENISON ST HAMILTON | Unit 1 | Water Ingress | Marty arranging access for late next week | TJ | April
35 | DENISON ST HAMILTON | Unit 9 & 12 | Water Ingress | Marty arranging access for late next week | TJ | April
36 | DENISON ST HAMILTON | Planterboxes | Leaking Planterboxes | Marty arranging access for late next week | TJ | April
37 | DENISON ST HAMILTON | Common area | Drummy Tiles | Contact TDX to repair & install expansion joint - Left message try again | TDX | April
38 | MILLHORN | Unit 104 | Replace Kickplate under Dishwasher | Secure kickplate in position | Marty | June
39 | MILLHORN | Unit 104 | Door Binding Main Bedroom | Adjust Door to suit | Marty | June
40 | MILLHORN | Unit 104 | Entry Door to 2nd Bedroom won't lock adjust striker plate | Adjust Doorstriker plate | Marty | June
41 | MILLHORN | Unit 304 | Water penetrating
42 | MILLHORN
43 | MILLHORN
44 | MILLHORN | 304 | Water leak | Investigate & Repair - Flood test Mould treatment left to do next week | Marty | 2020-04-03
45 | MILLHORN | Window lvl 1 | Water leak | Investigate & Repair - Flood test | Marty | 2020-04-03
46 | EVOLVE | Courtyards | Carpentry works | Isaac directing Marty to do works | Marty | Completed

## 10-6-20
Date: 2/4/2020 | SITE | AREA/UNIT | ISSUE | ACTIONS | RESPONSIBILITY | PROPOSED DATE | COMPLETED DATE
1 | AERO | Unit 1103 | Water ingress x 2 | Frontline Dan & Steve to inspect - 4 dry days required | TJ | 2020-06-26
2 | AERO | ROOF Storage GWH FM Department | Storage required for FM Department | Clean room out and Install Shelves and Racks for FM Department - Marty to tidy and finish room | Marty | 2020-03-12 | Commenced
3 | AERO | Unit 402 | Window in living room leaking | Inspect & report back 3 windows remaining | Marty | 2020-04-03
4 | AERO | HWS Plant Room | Wall section requires rectification FN:3899 | Marty to sheet walls | Marty | June
5 | AERO | FM Plant | Make into store | Marty to fit out for Facility team | Marty | June
6 | AERO | Bin Room | Water damage - Re-epoxy | Identify leak, repaint epoxy surface | Marty
7 | AERO | 603/770 Hunter st | Dishwasher | Investigate issue | Marty | June
8 | WATERVIEW | Carpark | Concrete dusting | Test Evo-Seal product -TJ Follow up with epoxy and Rick Harris 4 day required | Marty
9 | WATERVIEW | Unit 8 Carpark | Drencher and Curtain | Shaun Wallace and Alan Sacarro (Fire engineer) communicating for solution, HWC to supply Pressure at Street Level, PCA engaged Purchase Order HAS BEEN ISSUED | RB | March
10 | WATERVIEW | L2 Common Rooves & Soffitt | non compliant roof & no expansion joints in Soffitt | Allerce engaged to do works - Require dry period | RB
11 | THROSBY ST | 103/27 Lot 6 | Water & Mould Issues | installs back pans,deck tie and press tight - Marty to contact Chris Lawler re access | Marty | Early May
12 | SOHO FERN ST | 404/11 | No overflow | Marty to schedule spitter install | Marty | 2020-03-26
13 | MAITLAND ROAD ISLINGTON | 401/54 Unit 102 & 402 - 54 | Water & Mould Issues, Water issues planterboxes | Taylor to recommend contractor - 4.30pm inspection today Check 401 Marty following up with Tenant | Marty
14 | MAITLAND ROAD ISLINGTON | East & West prefab walls | Install Backing rod and Mastik | Marty to ensure 3 point system anchoring is adhered to: Reece wall 3 backing rods to be installed behind existing scaffolding | Marty
15 | CENTRALE | Lvl 2&3 | Water Leak | Rectify ridges & Front strip to prevent water ingress | Marty | 2020-04-03
16 | CENTRALE | 305A | Cladding leak | Investigate & Repair - Marty Arrange to inspect - Allerce Marty to follow up | Marty
17 | CENTRALE | A303 | Common area wall warp, carpet soiled | Investigate & Repair - Marty Arrange to inspect Tenant advised no issue | Marty
18 | CENTRALE | A302 | Water leak | Investigate & Repair - Marty Arrange to inspect | Marty | Completed
19 | CENTRALE | B303 | Water damage Kitchen | Investigate & Repair - Marty Arrange to inspect | Marty
20 | CENTRALE | B103 | Ensuite Bathroom | Marty Arrange to inspect | Marty
21 | CENTRALE | A106 | Cracking | Investigate & Repair - Marty Arrange to inspect | Marty
22 | CENTRALE | A303 | Mould smell outside 303 | Investigate & Repair - Marty Arrange to inspect | Marty
23 | CENTRALE | A303 | Window leak | Investigate & Repair - Marty Arrange to inspect | Marty
24 | CENTRALE | B202 | Cracking | Investigate & Repair - Repaired ready to paint | Marty
25 | CENTRALE | B202 | Loose tiles on Balcony | Investigate & Repair - Marty Arrange to inspect | Marty | Completed
26 | MILLHORN | Apt 304 | Water leak | Investigate & Repair - Flood test | Marty | 2020-04-03
27 | CENTRALE | 301B | Expansion Joints | GWH to gain access and inspect - Roof leak today | Marty | Early March
28 | EASTSIDE | Unit 203 | Water issues | Onyx to seal Eastern and North nib wall joints | Onyx | June
29 | EASTSIDE | Unit 603 | Water Leak x 2 | Taylor arranging EWP - ONYX | TJ | Early March | Wait after Restrictions have been lifted
30 | EASTSIDE | 702 | Inspect balcony above 603 for any water issues | Taylor given Natasha Contact | MR & TJ | April | Wait after Restrictions have been lifted
31 | EASTSIDE | Unit 310 | Water Leak | Marty to check balcony of unit above - await COVID19 restrictions to be lifted | MR | April | Wait after Restrictions have been lifted
32 | GREENSIDE | 2:04 | Water Sealing | Redo Bathroom - Confirm with Jono after his inspection Access required to inspect Talor actioning now | RB & JONO | Early March
33 | GREENSIDE |  | Cracks | Epoxy preferred less downtime, Tiling would be ideal whether Tiles with linear drains installed at each entry door x 4 are an acceptable solution - Confirm this is acceptable Confirm with Jono after his inspection | RB & JONO
34 | CIVILAB |  | Shelves & Room | Marty to contact Allerce | Marty | 2020-04-03
35 | DENISON ST HAMILTON | Unit 1 | Water Ingress | Marty arranging access for late next week | TJ | April
36 | DENISON ST HAMILTON | Unit 9 & 12 | Water Ingress | Marty arranging access for late next week | TJ | April
37 | DENISON ST HAMILTON | Planterboxes | Leaking Planterboxes | Marty arranging access for late next week | TJ | April
38 | DENISON ST HAMILTON | Common area | Drummy Tiles | Contact TDX to repair & install expansion joint - Left message try again | TDX | April
39 | DENISON ST HAMILTON | Unit 101 | Garden Bed outside Unit 8 Leaking | Contact TDX to repair & install expansion joint - Left message try again | TDX | April
40 | MILLHORN | Unit 104 | Replace Kickplate under Dishwasher | Secure kickplate in position | Marty | June
41 | MILLHORN | Unit 104 | Door Binding Main Bedroom | Adjust Door to suit | Marty | June
42 | MILLHORN | Unit 104 | Entry Door to 2nd Bedroom won't lock adjust striker plate | Adjust Doorstriker plate | Marty | June
43 | MILLHORN | Unit 304 | Water penetrating NE corner 2nd Bedroom | Seal all potential crevices | Marty | June
44 | MILLHORN | Garbage Chute | Garbage odours | Check fans are working | Taylor & Marty | June
45 | MILLHORN | Unit 402 | Eastern balcony balustrade | Poor render finish & sealant - Redo | Marty | June
46 | MILLHORN | 304 | Water leak | Investigate & Repair - Flood test Mould treatment left to do next week | Marty | 2020-04-03
47 | MILLHORN | Window lvl 1 | Water leak | Investigate & Repair - Flood test | Marty | 2020-04-03
48 | MILLHORN | Unit 403 | Sharp striker plates | File down any sharp edges | Marty | June
49 | MILLHORN | Unit 405 | Ensuite minor corrosion to door jamb & sealant separation | Apply anti corrosion solution to door frame, redo sealant | Marty | June
50 | MILLHORN | Roof | Roof sheet creased | Repair | Taylor & Marty | June
51 | MILLHORN | Level 5 | SE vegetable garden terrace | Remove packers to Level 7 Balcony balustrade | Marty | June
52 | MILLHORN | Level 5 | SE vegetable garden terrace | Leaching apparent head of Level 6 pre-cast panel | Hunter Precast | June
53 | MILLHORN | Level 1 & Ground Floor Carpark | Premature corrosion on panel brackets | Re-epoxy brackets | Marty | June
54 | MILLHORN | Ground Floor LH Toilet | Remove plastic from mirror surrounds | Remove plastics | Marty | June
55 | MILLHORN | Level 6 Fire stairs | door frame | Repair door frame | Marty | June

## 29-6-20
Date: 29/6/2020 | SITE | AREA/UNIT | ISSUE | ACTIONS | RESPONSIBILITY | PROPOSED DATE | COMPLETED DATE
1 | AERO | Unit 1103 | Water ingress x 2 | Frontline Dan & Steve to inspect - 4 dry days required | TJ | 2020-06-30
2 | AERO | ROOF Storage GWH FM Department | Storage required for FM Department | Clean room out and Install Shelves and Racks for FM Department - Marty to tidy and finish room | Marty | 2020-03-12 | Commenced
4 | AERO | HWS Plant Room | Wall section requires rectification FN:3899 | Marty to sheet walls | Marty | June
6 | AERO | Bin Room | Water damage - Re-epoxy | Identify leak, repaint epoxy surface - Quote received | Marty
7 | AERO | 603/770 Hunter st | Dishwasher | Investigate issue - awaiting panel Marty will follow up | Marty | June
8 | WATERVIEW | Carpark | Concrete dusting | Test Evo-Seal product -TJ Follow up with epoxy and Rick Harris 4 day required | Marty
9 | WATERVIEW | Unit 103 | Remove rust and paint on Balcony | Marty to liaise | Marty
10 | WATERVIEW | Unit 8 Carpark | Drencher and Curtain | Shaun Wallace and Alan Sacarro (Fire engineer) communicating for solution, HWC to supply Pressure at Street Level, PCA engaged Purchase Order HAS BEEN ISSUED | RB | March
11 | WATERVIEW | L2 Common Rooves & Soffitt | non compliant roof & no expansion joints in Soffitt | Allerce & Freestyle engaged to do works - Require dry period | RB
12 | THROSBY ST | 103/27 Lot 6 | Water & Mould Issues | installs back pans,deck tie and press tight - Marty to contact Chris Lawler re access | Marty | Early May
13 | SOHO FERN ST | 404/11 | No overflow | Marty to contact Kane final part of waterproofing to be done | Marty | 2020-03-26
14 | MAITLAND ROAD ISLINGTON | 401/54 Unit 102 & 402 - 54 | Water & Mould Issues, Water issues planterboxes | Taylor to recommend contractor - 4.30pm inspection today Check 401 Marty following up with Tenant | Marty
15 | MAITLAND ROAD ISLINGTON | East & West prefab walls | Install Backing rod and Mastik | Marty to ensure 3 point system anchoring is adhered to: Reece wall 3 backing rods to be installed behind existing scaffolding | Marty
16 | CENTRALE | Lvl 2&3 | Water Leak | Rectify ridges & Front strip to prevent water ingress | Marty | 2020-04-03
17 | CENTRALE | 305A | Cladding leak | Investigate & Repair - Marty Arrange to inspect - Allerce Marty to follow up | Marty
18 | CENTRALE | A303 | Common area wall warp, carpet soiled | Investigate & Repair - Marty Arrange to inspect Tenant advised no issue | Marty
19 | CENTRALE | A302 | Water leak | Investigate & Repair - Marty Arrange to inspect | Marty | Completed
20 | CENTRALE | B303 | Water damage Kitchen | Investigate & Repair - Marty Arrange to inspect | Marty
21 | CENTRALE | B103 | Ensuite Bathroom | Marty Arrange to inspect | Marty
22 | CENTRALE | A106 | Cracking | Investigate & Repair - Marty Arrange to inspect | Marty
23 | CENTRALE | A303 | Mould smell outside 303 | Investigate & Repair - Marty Arrange to inspect | Marty
24 | CENTRALE | A303 | Window leak | Investigate & Repair - Marty Arrange to inspect | Marty
25 | CENTRALE | B202 | Cracking | Investigate & Repair - Repaired ready to paint | Marty
26 | MILLHORN | Apt 304 | Water leak | Investigate & Repair - Flood test | Marty | 2020-04-03
27 | MILLHORN | L1 & L2 | Water leak | Investigate | Marty
28 | CENTRALE | 301B | Expansion Joints | GWH to gain access and inspect - Roof leak today | Marty | Early March
29 | EASTSIDE | Unit 203 | Water issues | Onyx to seal Eastern and North nib wall joints | Onyx | June
30 | EASTSIDE | Unit 603 | Water Leak x 2 | Taylor arranging EWP - ONYX | TJ | Early March | Wait after Restrictions have been lifted
31 | EASTSIDE | 702 | Inspect balcony above 603 for any water issues | Taylor given Natasha Contact | MR & TJ | April | Wait after Restrictions have been lifted
32 | EASTSIDE | Unit 310 | Water Leak | Marty to check balcony of unit above - await COVID19 restrictions to be lifted | MR | April | Wait after Restrictions have been lifted
33 | GREENSIDE | 2:04 | Water Sealing | Redo Bathroom - Confirm with Jono after his inspection Access required to inspect Talor actioning now - Painting Required | RB, Taylor & JONO | Early March
34 | GREENSIDE |  | Cracks | Epoxy preferred less downtime, Tiling would be ideal whether Tiles with linear drains installed at each entry door x 4 are an acceptable solution - Confirm this is acceptable Confirm with Jono after his inspection | RB, Taylor & JONO
35 | CIVILAB |  | Shelves & Room | Marty to contact Allerce | Marty | 2020-04-03
36 | DENISON ST HAMILTON | Unit 1 | Water Ingress | Marty arranging access for late next week | TJ | April
37 | DENISON ST HAMILTON | Unit 9 & 12 | Water Ingress | Marty arranging access for late next week | TJ | April
38 | DENISON ST HAMILTON | Planterboxes | Leaking Planterboxes | Marty arranging access for late next week | TJ | April
39 | DENISON ST HAMILTON | Common area | Drummy Tiles | Contact TDX to repair & install expansion joint - Left message try again | TDX | April
40 | DENISON ST HAMILTON | Unit 101 | Garden Bed outside Unit 8 Leaking | Contact TDX to repair & install expansion joint - Left message try again | TDX | April
41 | Thornton
42 | Spitfire
43 | MILLHORN | Unit 104 | Replace Kickplate under Dishwasher | Secure kickplate in position | Marty | June
44 | MILLHORN | Unit 104 | Door Binding Main Bedroom | Adjust Door to suit | Marty | June
45 | MILLHORN | Unit 104 | Entry Door to 2nd Bedroom won't lock adjust striker plate | Adjust Doorstriker plate | Marty | June
46 | MILLHORN | Unit 304 | Water penetrating NE corner 2nd Bedroom | Seal all potential crevices | Marty | June
47 | MILLHORN | Garbage Chute | Garbage odours | Check fans are working | Taylor & Marty | June
48 | MILLHORN | Unit 402 | Eastern balcony balustrade | Poor render finish & sealant - Redo | Marty | June
49 | MILLHORN | 304 | Water leak | Investigate & Repair - Flood test Mould treatment left to do next week | Marty | 2020-04-03
50 | MILLHORN | Window lvl 1 | Water leak | Investigate & Repair - Flood test | Marty | 2020-04-03
51 | MILLHORN | Unit 403 | Sharp striker plates | File down any sharp edges | Marty | June
52 | MILLHORN | Unit 405 | Ensuite minor corrosion to door jamb & sealant separation | Apply anti corrosion solution to door frame, redo sealant | Marty | June
53 | MILLHORN | Roof | Roof sheet creased | Repair | Taylor & Marty | June
54 | MILLHORN | Level 5 | SE vegetable garden terrace | Remove packers to Level 7 Balcony balustrade | Marty | June
55 | MILLHORN | Level 5 | SE vegetable garden terrace | Leaching apparent head of Level 6 pre-cast panel | Hunter Precast | June
56 | MILLHORN | Level 1 & Ground Floor Carpark | Premature corrosion on panel brackets | Re-epoxy brackets | Marty | June
57 | MILLHORN | Ground Floor LH Toilet | Remove plastic from mirror surrounds | Remove plastics | Marty | June
58 | MILLHORN | Level 6 Fire stairs | door frame | Repair door frame | Marty | June

## 9-7-20
Date: 9/7/2020 | SITE | AREA/UNIT | ISSUE | ACTIONS | RESPONSIBILITY | PROPOSED DATE | COMPLETED DATE
1 | AERO | Unit 1103 | Water ingress x 2 | Flood test required to confirm works | TJ | 2020-06-30
2 | AERO | ROOF Storage GWH FM Department | Storage required for FM Department | Clean room out and Install Shelves and Racks for FM Department - Marty to tidy and finish room | Marty | 2020-03-12 | Commenced
3 | AERO | HWS Plant Room | Wall section requires rectification FN:3899 | Marty to sheet walls | Marty | June
4 | AERO | Bin Room | Water damage - Re-epoxy | Identify leak, repaint epoxy surface - Quote received | Marty
5 | AERO | 603/770 Hunter st | Dishwasher | Investigate issue - awaiting panel Marty will follow up | Marty | June
6 | WATERVIEW | Carpark | Concrete dusting | Markham to provide 2 options | Marty
7 | WATERVIEW | Unit 103 | Remove rust and paint on Balcony | Marty to liaise | Marty
8 | WATERVIEW | Unit 8 Carpark | Drencher and Curtain | Decision to be made regarding direction with this | RB | March
9 | WATERVIEW | L2 Common Rooves & Soffitt | non compliant roof & no expansion joints in Soffitt | Allerce & Freestyle engaged to do works - Require dry period | RB
10 | THROSBY ST | 103/27 Lot 6 | Water & Mould Issues | installs back pans,deck tie and press tight - Marty to contact Chris Lawler re access | Marty | Early May
11 | SOHO FERN ST | 404/11 | No overflow | Marty to contact Kane final part of waterproofing to be done | Marty | 2020-03-26
12 | MAITLAND ROAD ISLINGTON | East & West prefab walls | Install Backing rod and Mastik | Marty to ensure 3 point system anchoring is adhered to: Reece wall 3 backing rods to be installed behind existing scaffolding | Marty
13 | CENTRALE | Lvl 2&3 | Water Leak | Rectify ridges & Front strip to prevent water ingress | Marty | 2020-04-03
14 | CENTRALE | 305A | Cladding leak | Investigate & Repair - Marty Arrange to inspect - Allerce Marty to follow up | Marty
15 | CENTRALE | A303 | Common area wall warp, carpet soiled | Investigate & Repair - Marty Arrange to inspect Tenant advised no issue | Marty
16 | CENTRALE | B303 | Water damage Kitchen | Investigate & Repair - Marty Arrange to inspect | Marty
17 | CENTRALE | B103 | Ensuite Bathroom | Marty Arrange to inspect | Marty
18 | CENTRALE | A106 | Cracking | Investigate & Repair - Marty Arrange to inspect | Marty
19 | CENTRALE | A303 | Mould smell outside 303 | Investigate & Repair - Marty Arrange to inspect | Marty
20 | CENTRALE | A303 | Window leak | Investigate & Repair - Marty Arrange to inspect | Marty
21 | CENTRALE | B202 | Cracking | Investigate & Repair - Repaired ready to paint | Marty
22 | MILLHORN | Apt 304 | Water leak | Investigate & Repair - Flood test | Marty | 2020-04-03
23 | MILLHORN | L1 & L2 | Water leak | Investigate | Marty
24 | EASTSIDE | Unit 603 | Water Leak x 2 | Taylor arranging EWP - ONYX | TJ | Early March | Wait after Restrictions have been lifted
25 | EASTSIDE | 702 | Inspect balcony above 603 for any water issues | Taylor given Natasha Contact | MR & TJ | April | Wait after Restrictions have been lifted
26 | EASTSIDE | Unit 310 | Water Leak | Marty to check balcony of unit above - await COVID19 restrictions to be lifted | MR | April | Wait after Restrictions have been lifted
27 | GREENSIDE | 2:04 | Water Sealing | Redo Bathroom - Confirm with Jono after his inspection Access required to inspect Talor actioning now - Painting Required | RB, Taylor & JONO | Early March
28 | GREENSIDE |  | Cracks | Epoxy preferred less downtime, Tiling would be ideal whether Tiles with linear drains installed at each entry door x 4 are an acceptable solution - Confirm this is acceptable Confirm with Jono after his inspection | RB, Taylor & JONO
29 | CIVILAB |  | Shelves & Room | Marty to contact Allerce | Marty | 2020-04-03
30 | DENISON ST HAMILTON | Unit 1 | Water Ingress | Marty arranging access for late next week | TJ | April
31 | DENISON ST HAMILTON | Unit 9 & 12 | Water Ingress | Marty arranging access for late next week | TJ | April
32 | DENISON ST HAMILTON | Planterboxes | Leaking Planterboxes | Marty arranging access for late next week | TJ | April
33 | DENISON ST HAMILTON | Common area | Drummy Tiles | TDX updated quotations - Newcastle Tile will provide 2 options | TDX | April
34 | DENISON ST HAMILTON | Unit 101 | Garden Bed outside Unit 8 Leaking | TDX updated quotations - Newcastle Tile will provide 2 options | TDX | April
35 | MILLHORN | Unit 104 | Replace Kickplate under Dishwasher | Secure kickplate in position | Marty | June
36 | MILLHORN | Unit 104 | Door Binding Main Bedroom | Adjust Door to suit | Marty | June
37 | MILLHORN | Unit 104 | Entry Door to 2nd Bedroom won't lock adjust striker plate | Adjust Doorstriker plate | Marty | June
38 | MILLHORN | Unit 304 | Water penetrating NE corner 2nd Bedroom | Seal all potential crevices | Marty | June
39 | MILLHORN | Garbage Chute | Garbage odours | Check fans are working | Taylor & Marty | June
40 | MILLHORN | Unit 402 | Eastern balcony balustrade | Poor render finish & sealant - Redo | Marty | June
41 | MILLHORN | 304 | Water leak | Investigate & Repair - Flood test Mould treatment left to do next week | Marty | 2020-04-03
42 | MILLHORN | Window lvl 1 | Water leak | Investigate & Repair - Flood test | Marty | 2020-04-03
43 | MILLHORN | Unit 403 | Sharp striker plates | File down any sharp edges | Marty | June
44 | MILLHORN | Unit 405 | Ensuite minor corrosion to door jamb & sealant separation | Apply anti corrosion solution to door frame, redo sealant | Marty | June
45 | MILLHORN | Roof | Roof sheet creased | Repair | Taylor & Marty | June
46 | MILLHORN | Level 5 | SE vegetable garden terrace | Remove packers to Level 7 Balcony balustrade | Marty | June
47 | MILLHORN | Level 5 | SE vegetable garden terrace | Leaching apparent head of Level 6 pre-cast panel | Hunter Precast | June
48 | MILLHORN | Level 1 & Ground Floor Carpark | Premature corrosion on panel brackets | Re-epoxy brackets | Marty | June
49 | MILLHORN | Ground Floor LH Toilet | Remove plastic from mirror surrounds | Remove plastics | Marty | June
50 | MILLHORN | Level 6 Fire stairs | door frame | Repair door frame | Marty | June

## 15-9-20
2020-09-15 | STATUS | PRIORITY | SITE | AREA/UNIT | ISSUE | ACTIONS | RESPONSIBILITY | PROPOSED DATE | COMPLETED DATE
1 | Completed |  | AERO | Unit 1103 | Water ingress x 2 | 7 windows near Bedroom 2 removed, insulated and reinstated - Monitor condensation | RB | 2020-09-07 | 2020-09-08
2 | To be completed | 3 | AERO | ROOF Storage GWH FM Department | Storage required for FM Department | Clean room out and Install Shelves and Racks for FM Department - Marty to tidy and finish room | Marty | 2020-03-12 | Commenced
3 | To be completed | 2 | AERO | HWS Plant Room | Wall section requires rectification FN:3899 | Marty to sheet walls | Marty | June
4 | Hold Off |  | AERO | Bin Room | Water damage - Re-epoxy | Identify leak, repaint epoxy surface - Quote received | Marty
5 | To be completed | 2 | AERO | 603/770 Hunter st | Dishwasher | Investigate issue - awaiting panel Marty will follow up | Marty | June
6 | Hold Off |  | WATERVIEW | Carpark | Concrete dusting | Markham to provide 2 options | Marty
7 | To be completed | 1 | WATERVIEW | Unit 204 Reinstate Ceiling | Water damage and inspection holes to be covered | Allerce engaged to do works - Awaiting reports that roofing has been successful
8 | To be completed | 1 | WATERVIEW | Unit 103 | Remove rust and paint on Balcony | Marty to liaise | Marty
9 | To be completed | 1 | WATERVIEW | Unit 8 Carpark | Drencher and Curtain | Decision to be made regarding direction with this | RB | October
10 | Completed |  | WATERVIEW | L2 Common Roof pitch non-compliant | non compliant roof pitch | Freestyle engaged to do works - Require dry period Cliplock roof sheets installed 3.0degree rake achieved | RB | 2020-09-01
11 | To be completed | 1 | WATERVIEW | L2 Common Soffitt | non compliant roof & no expansion joints in Soffitt | Allerce engaged to do works - Awaiting reports that roofing has been successful | RB
12 | To be completed | 1 | THROSBY ST | 103/27 Lot 6 | Water & Mould Issues | installs back pans,deck tie and press tight - Marty to contact Chris Lawler re access | Marty | Early May
13 | To be completed | 1 | THROSBY ST | 101/27 Lot 6 | Water & Mould Issues | Inspect & Rectify | Marty | Early May
14 | Completed |  | SOHO | 101/54 & 103/54 cladding rusting | Cladding issue | Rustproof cladding
15 | Completed |  | SOHO | Level 1 Courtyard | Planterbox cappings corroded | Rustproof cladding
16 | To be completed | 1 | SOHO | Courtyard elevation Fern St side | Remove bubbling Efflorescence | Treat with Evosaltaway
17 | Completed |  | SOHO FERN ST | 404/11 | No overflow | Marty to contact Kane final part of waterproofing to be done | Marty | 2020-03-26
18 | To be completed | 1 | SOHO FERN ST | Light weight construction Courtyards | Water leaks | Marty to liaise with ONYX | Marty | September
19 | To be completed | 1 | SOHO FERN ST | Lower Ground Floor Foyer | Patch hole | Marty to patch hole in suspended ceiling above entrance | Marty | September
20 | To be completed | 1 | SOHO FERN ST | Carpark | Repair leak from copper pipe | Marty to ensure leak has been rectifioed possible Mullanes to rectify | Marty | September
21 | Completed |  | SOHO MAITLAND ROAD ISLINGTON | East & West prefab walls | Install Backing rod and Mastik | Marty to ensure 3 point system anchoring is adhered to: Reece wall 3 backing rods to be installed behind existing scaffolding | Marty | August
22 | To be completed | 1 | CENTRALE | Lvl 2&3 | Water Leak | Rectify ridges & Front strip to prevent water ingress | Marty | 2020-04-03
23 | To be completed | 1 | CENTRALE | 305A | Cladding leak | Investigate & Repair - Marty Arrange to inspect - Allerce Marty to follow up | Marty
24 | To be completed | 1 | CENTRALE | A303 | Common area wall warp, carpet soiled | Investigate & Repair - Marty Arrange to inspect Tenant advised no issue | Marty
25 | To be completed | 1 | CENTRALE | B303 | Water damage Kitchen | Investigate & Repair - Marty Arrange to inspect | Marty
26 | To be completed | 1 | CENTRALE | B103 | Ensuite Bathroom | Marty Arrange to inspect | Marty
27 | To be completed | 1 | CENTRALE | A106 | Cracking | Investigate & Repair - Marty Arrange to inspect | Marty
28 | To be completed | 1 | CENTRALE | A303 | Mould smell outside 303 | Investigate & Repair - Marty Arrange to inspect | Marty
29 | To be completed | 1 | CENTRALE | A303 | Window leak | Investigate & Repair - Marty Arrange to inspect | Marty
30 | To be completed | 1 | CENTRALE | B202 | Cracking | Investigate & Repair - Repaired ready to paint | Marty
31 | To be completed | 1 | CENTRALE | 201/67 | Flooring | Rectify flooring - Matt Brady | Marty
32 | To be completed | 1 | CENTRALE | 203/65 | Water issue | Investigate & Repair | Marty
33 | To be completed | 1 | EASTSIDE | Unit 603 | Water Leak x 2 | Access required to unit above | TJ | Early March | Wait after Restrictions have been lifted
34 | To be completed | 1 | EASTSIDE | 702 | Inspect balcony above 603 for any water issues | Taylor given Natasha Contact | MR & TJ | April | Wait after Restrictions have been lifted
35 | To be completed | 1 | EASTSIDE | Unit 310 | Water Leak | Marty to check balcony of unit above - await COVID19 restrictions to be lifted | MR | April | Wait after Restrictions have been lifted
36 | To be completed | 1 | EASTSIDE | Unit 203 | Water Leak | Marty to check balcony of unit above - await COVID19 restrictions to be lifted | MR | April | Wait after Restrictions have been lifted
37 | To be completed | 3 | CIVILAB |  | Shelves & Room | Marty to contact Allerce | Marty | 2020-04-03
38 | To be completed | 3 | CIVILAB |  | Lab Door required with window insert | Quote on Door
39 | To be completed | 1 | DENISON ST HAMILTON | Unit 1 | Water Ingress | Marty arranging access for late next week | TJ | April
40 | To be completed | 1 | DENISON ST HAMILTON | Unit 9 & 12 | Water Ingress | Marty arranging access for late next week | TJ | April
41 | Completed |  | DENISON ST HAMILTON | Planterboxes | Leaking Planterboxes | Installed 12 caps to Divider fence, sealed all penetrations, to be monitored in carpark | RB | August
42 | To be completed | 1 | DENISON ST HAMILTON | Common area | Drummy Tiles | Newcastle tile to replace all drummy tiles | Newcastle Tiles | September
43 | To be completed | 1 | DENISON ST HAMILTON | Unit 101 | Garden Bed outside Unit 8 Leaking | TDX updated quotations - Newcastle Tile will provide 2 options Flood test | Newcastle Tiles | September
44 | To be completed | 1 | DENISON ST HAMILTON | all balconies | seal around sliding doors | NJD to seal area | Newcastle Tiles | September
45 | Completed |  | MILLHORN | Apt 304 | Water leak | Investigate & Repair - Flood test | Marty | 2020-04-03
46 | To be completed | 1 | MILLHORN | L1 & L2 | Water leak | Investigate | Marty
47 | To be completed | 2 | MILLHORN | Carpark | Rusty brackets on Panels | Apply rust remover | Marty
48 | To be completed | 2 | MILLHORN | Unit 104 | Replace Kickplate under Dishwasher | Secure kickplate in position | Marty | June
49 | To be completed | 2 | MILLHORN | Unit 104 | Door Binding Main Bedroom | Adjust Door to suit | Marty | June
50 | To be completed | 2 | MILLHORN | Unit 104 | Entry Door to 2nd Bedroom won't lock adjust striker plate | Adjust Doorstriker plate | Marty | June
51 | Completed |  | MILLHORN | Unit 304 | Water penetrating NE corner 2nd Bedroom | Seal all potential crevices | Marty | June
52 | Completed |  | MILLHORN | Garbage Chute | Garbage odours | Check fans are working | Taylor & Marty | June
53 | To be completed | 1 | MILLHORN | Unit 402 | Poor finish | Poor render finish & sealant - Redo | Marty | June
54 | To be completed | 1 | MILLHORN | 304 | Water issue | Investigate & Repair - Flood test Mould treatment left to do next week | Marty | 2020-04-03
55 | To be completed | 1 | MILLHORN | Window lvl 1 | Water issue | Investigate & Repair - Flood test | Marty | 2020-04-03
56 | To be completed | 2 | MILLHORN | Unit 403 | Strike plates | File down any sharp edges | Marty | June
57 | To be completed | 1 | MILLHORN | Unit 405 | Corrosion | Apply anti corrosion solution to door frame, redo sealant | Marty | June
58 | Completed |  | MILLHORN | Roof | Repair creases | Repair | Taylor & Marty | August
59 | To be completed | 2 | MILLHORN | Level 5 | Remove packers | Remove packers to Level 7 Balcony balustrade | Marty | June
60 | To be completed | 2 | MILLHORN | Level 5 | Investigate | Leaching apparent head of Level 6 pre-cast panel | Hunter Precast | June
61 | To be completed | 1 | MILLHORN | Level 1 & Ground Floor Carpark | Rusting brackets | Re-epoxy brackets | Marty | June
62 | To be completed | 1 | MILLHORN | Ground Floor LH Toilet | Remove plastic | Remove plastics | Marty | June
63 | To be completed | 1 | MILLHORN | Level 6 Fire stairs | Corrosion | Repair door frame | Marty | June